## Sheet1
Project Summary |  |  | Test Results Summary
Project Code | FQM |  | Total No. of Test cases | 11
Application Name | Access |  | Total No. of Test cases Executed | 11
Feature/Story | Bulk upload for cycle extension for individual Manager(s)
Release / Sprint | Epic 2 |  | Pass | 11
Test Environment | QA |  | Fail | 0
Test Case Number | Test cases title | Test Steps | Expected Results | Actual Results | Results Pass/Fail | Comment | Execution date
1 | Verify cycle extension for user/Manager journey | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login" 5. Go to the Assess admin application and click on Room management on the left hand navigation. 6. Click on Room extension. 6. Click on download. 7. Enter the GID of user who have not submitted the self assessment . 8. Click on upload Excel. 9. Click on the calendar icon to extend the date for particular user . 10. Click on Select user/Manager drop down. 11. Click on submit. 12. Log into Assess application as the user and submit the self assessment | 1. User should land to the Assess Admin application. 2. User should navigate to the Room extension page. 3. User should able to download the excel . 4. User should able to enter the GID in Excel. 5. User should able to upload the excel. 6. User should get the calendar and able to select the date. 7. User should able to select the user/manager option from the drop down. 8. User should able to do the Self or D.R. Assessment. | 1. User landed to the Assess Admin page. 2.User has been navigated to Room extension page. 3.User downloaded the excel file. 4. User Entered the GID . 5. user selected the date from calender. 6. User selected as expected. 7. User have been able to do the Assessment. | Pass | AC-429 | 2022-05-04
2 | Verify that specific user/Manager journey date should be extended when rooms are closed | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login" 5. Go to the Assess admin application and click on Room management on the left hand navigation. 6. Click on 'Manage Room journey' 7. Click on Edit. 8. Click on 'status' under room managment journey. 9. Click on update. 10 . Agian go to Room management, Click on Room extension. 11. Click on download. 12. Enter the GID of user who have not submitted the self assessment . 13. Click on upload Excel. 14. Click on the calander icon to extend the date for particular user . 15. Click on Select user/Manager drop down. 16. Click on submit. 17. log in to the assess application with the manager ID who room closure date was extended. 18. Manager completes their DR Assessment | 1. User should land to the Assess Admin application. 2. Room management journey page should be displayed with the cycle name, journey name , status and also period. 3. User should be able to Edit the room journey for user and manager. 4. User should be able to change the status in room journey. 5. user should be able to update or cancel the room journey. 6. User should navigate to the Room extension page. 7. User should able to download the excel . 8. User should able to enter the GID in Excel. 9. User should able to upload the excel. 10. User should get the calendar and able to select the date. 11. User should able to select the user/manager option in drop down. 12. User should able to complete their D.R. Assessment who have submitted their Self Assessment. | 1. User landed to the Assess Admin page. 2. Journey page displayed. 3. User edited the room journey. 4. User has changed the status in room journey. 5. Working as expected. 6. Room extension page displayed to the user. 7. User Entered the GID . 8. User uploaded the excel. 9. User selected the date from calender. 10. User should able to select the user/manager option in drop down. 11. User started the assessment. | Pass |  | 2022-05-04
3 | Verify that other user/manager journey date should not be extended when room are closed. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login" 5. Go to the Assess admin application and click on Room management on the left hand navigation. 6. Click on 'Room management journey' 7. Click on Edit. 8. Click on 'status' under room management journey. 9. Click on update. 10 . Again go to Room management, Click on Room extension. 11. Click on download. 12. Enter the GID of user who have not submitted the self assessment . 13. Click on upload Excel. 14. Click on the calendar icon to extend the date for particular user . 15. Click on Select user/Manager drop down. 16. Click on submit. | 1. User should land to the Assess Admin application. 2. Room management journey page should be displayed with the cycle name, journey name, status and also period. 3. User should be able to Edit the room journey for user and manager. 4. User should be able to change the status in room journey. 5. user should be able to update or cancel the room journey. 6. User should navigate to the Room extension page. 7. User should able to download the excel . 8. User should able to enter the GID in Excel. 9. User should able to upload the excel. 10. User should get the calendar Bizet and should able to select the particular date. 11. User should able to select the user/manager option in drop down. 12. User should able to click on upload. | 1. User landed to the Assess Admin page. 2. Journey page displayed. 3. User edited the room journey. 4. User has changed the status in room journey. 5. Working as expected. 6. Room extension page displayed to the user. 7. User Entered the GID . 8. User uploaded the excel. 9. User selected the date from calender. 10. User should able to select the user/manager option in drop down. 11. User started the assessment. | Pass |  | 2022-05-04
4 | Verify that manager should not able to do the D.R. assessment when the Self Assessment status is in-progress after extending the journey date. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the New Assess URL . 3. Enter the valid login credential. 4. Click on "Login" 5. In the start page , click on 'my team' 6. Select the particular user , whose assessment status is showing as in-progress. | 1. User should land to the start page. 2. User should land to the My team page. 3. User should not get the assessment page . | 1. User landed to the start page. 2. User navigated to my team page. 3. Working as expected. | Pass |  | 2022-05-04
6 | Verify that manager should not able to do the D.R assessment if their GID is not uploaded while extending the journey date. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the New Assess URL . 3. Enter the valid login credential. 4. Click on "Login" 5. In the start page , click on 'my team' 6. Select the particular user who have requested for journey extension. | 1. User should land to the start page. 2. My team page should be displayed. 3. User should not able to do the assessment. | 1. User landed to the start page. 2. User navigated to my team page. 3. Working as expected. | Pass |  | 2022-05-04
7 | Verify that if any D.R. have been transferred under other manager after completing the assessment, then that user should show under the transferred manager team and their assessment status also show accordingly. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login" 5. Go to User tab and click on view all user. 6. Select the GID and click on edit . 7.Go to supervisor section. 8. Enter the GID of the user to be transferred Under override supervisor section. 9. Click on update. 10. Now login into Assess application. 11. Enter the valid GID and password. 12. click on "Sign In" . 13. Go to My team and search for transferred employee name. 14. Also Manager can get their assessment status. | 1. User land to the Admin home page. 2. User should land to the Manage user page. 3. User should able to override the supervisor details. 4. User should able to click on update. 5. User should able to see the transferred member under My team page. 6. User should get the transferred D.R under their My team section.Their self assessment status should be displayed as completed. | 1. User landed to the Admin page. 2. User landed to the manage user page. 3. working as expected. 4. Working 5. Working as expected. 6. Working as expected. | Pass | AC-430 | 2022-05-04
8 | Verify that if any D.R. have been transferred under other manager before completing the assessment, then that user should show under the transferred manager team and manager can do their assessment. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login" 5. Go to User tab and click on view all user. 6. Select the GID and click on edit . 7.Go to supervisor section. 8. Enter the GID of the user to be transferred Under override supervisor section. 9. Click on update. 10. Now login as user in the Assess application. 11. Click on 'My Team' in the start page. 12. Select the particular user , whoes assessment need to be done. | 1. User land to the Admin home page. 2. User should land to the Manage user page. 3. User should able to override the supervisor details. 4. User should able to click on update. 5. User should able to see the transferred member under My team page. 6. Manager should able to do the assessment of tranfered D.R | 1. User landed to the Admin page. 2. User landed to the manage user page. 3. working as expected. 4. Working 5. Working as expected. 6. Working as expected. | Pass | AC-431 | 2022-05-04
9 | Verify that if user/manager have been disabled after extending the journey date | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login". 5. Go to users, click on 'view all user' 6. Change the mine status of particular user by admin setting. 7. Now Login into the Assess application . 8. Enter the valid GID and password. 9.Click on "Sign In" | 1. User should land to the start page. 2. User should land to 'Manage user' page 3. User whose status is disabled should not show for assessment. 4. For disabled user, it should show the error as per error state. | 1. User landed to the Admin page. 2. User landed to the manage user page. 3. working as expected. 4. Working | Pass |  | 2022-05-04
10 | Incorrect file format for cycle extension | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login". 5. Go to the Assess admin application and click on Room management on the left hand navigation. 6. Click on Room extension. 7. Click on Choose file (Other than excel) 8. Select the file other then excel. 9. Enter the room extension date. 10. Select user or manager from drop down. 11. Click on upload. | 1. Admin page should be displayed. 2. Room management page should be displayed. 3. Room extension Page should be displayed . 4. Application should show error message that selected file is not as xls,xlsx format. | 1. page displayed as expected. 2. page displayed. 3. Extension page displayed. 4. Showing error as expected. | Pass |  | 2022-05-04
11 | Incorrect coloumn name in excel for room extension. | Precondition : User should be live in Assess application. Test steps: 1. Open the browser . 2. Enter the Assess admin URL . 3. Enter the Assess admin login credential. 4. Click on "Login". 5. Go to the Assess admin application and click on Room management on the left hand navigation. 6. Click on Room extension. 7. Click on download 8. In the downloaded excel file , remove the coloum heading 9. Select the date for room extension. 10.Select User/ Manager and click on upload. | 1. User should get the error message as "Upload global ids to extend the closing date for Room" | 1. Error displayed. | Pass |  | 2022-05-04

## Sheet2
Note on A1: Prashanth Shashikumar: Cell formatting is in consistent.