## Sheet1
Project Summary |  |  | Test Results Summary
Project Code | FQM |  | Total No. of Test cases | 4
Application Name | Access |  | Total No. of Test cases Executed | 4
Feature/Story | Order of strengths on profile page
Release / Sprint | Epic 2 |  | Pass | 4
Test Environment | QA |  | Fail | 0
Test Case Number | Test cases title | Test Steps | Expected Results | Actual Results | Results Pass/Fail | Comment | Execution date
1 | Strength Card display in profile page(User Assessment) | Precondition: 1. User should be live user. 2. User should be eligible for the current cycle . Test Steps: 1. Launch the application using url 2. Enter valid credentials and login to the application 3. Click on Start text button in self assessment screen 4. User selects four strength cards, and click on Next text button 5. Click on save & Close button in classification screen 6. Click on Start text button in My profile 7. User selects the options (underused) for the first Strength card and click on confirm button and then click on Next text button 8. User select the option (Key) for the second strength card and click on confirm button and click on Next text button 9.User select the option (Critical) for the third strength card and click on confirm button and click on Next text button 10. User select the option (critical) for the fourth strength card and click on confirm button and click on Next text button 11. Third strength card ( This is the first strength selected as 'Critical' )will be redisplayed in Transformational screen 12. User choose the option " No, this strength is critical" and click on confirm button 13.Fourth strength card (this is the last strength selected as 'critical' based on above steps) will be redisplayed in Transformational screen 14. User choose option "Yes, this is a transformational strength" 15. User enter comments in the comment box ( How have you transformed the business with <Strength card name>?) 16. Click on Confirm button. | 1. Application Start page should be displayed 2. 'Self assessment start screen' should be displayed 3. Each strength card should be displayed in card mechanic intro screen 4. User should be navigated to My Profile 5. User selects 'Yes, this is a transformational strength', Comment box should be displayed and enabled to user inputs 6. Confirm button gets enabled 7.'Self assessment' should be submitted 8. System navigated to 'My Profile' screen after 2 second delay | 1. Landing page displayed. 2. Self assessment screen displayed 3. Strength card into screen displayed. 4. User navigated to My profile screen. 5. User selected the strength as Transformational and comment box displayed. | Pass |  | 2022-04-06
2 | Strength Card display in profile page(Manager Assessment) | Precondition: 1. User should be live user and should be eligible for the current cycle and User should be "Manager" 2.User should have completed self assessment 3.Atleast one his direct report (D.R)should have completed 'self assessment' Test Steps: 1. Launch the application using url 2. Enter valid credentials and login to the application 3. Click on 'My team' tab 4.User click on one of the D.R 5. User selects four strength cards, and click on Next text button 6. User selects the options (underused) for the first Strength card and click on confirm button and then click on Next text button 7. User select the option (Key) for the second strength card and click on confirm button and click on Next text button 8.User select the option (Critical) for the third strength card and click on confirm button and click on Next text button 9. User select the option (critical) for the fourth strength card and click on confirm button and click on Next text button 10. Check whether Defining Strengths as transformational Video auto plays 11. Third strength card ( This is the first strength selected as 'Critical' )will be redisplayed in Transformational screen 12. User choose the option " No, this strength is critical" and click on confirm button 13.Fourth strength card (this is the last strength selected as 'critical' based on above steps) will be redisplayed in Transformational screen 14. User choose option "Yes, this is a transformational strength" 15. User enter comments in the comment box ( How have you transformed the business with <Strength card name>?) 16. Click on Confirm button | 1. Application landing page should be displayed 2.D.R of users who have completed the 'Self assessment' should be displayed in 'My team' page 3. Card mechanic intro screen for the respective D.R should be displayed 4. User selects 'Yes, this is a transformational strength', Comment box should be displayed and enabled to user inputs 5. Confirm button gets enabled 6.'Manager assessment' should be submitted 7. System navigated to 'My Team' Screen after 2 seconds delay | 1. Landing page displayed. 2. Self assessment screen displayed 3. Strength card into screen displayed. 4. User navigated to My Team page. 5. User selected the strength as Transformational and comment box displayed. 6. Manager has submitted his D.R. assessment. | Pass |  | 2022-04-06
3 | Card strength display in profile page | Precondition: 1. User should be live user. 2. User should be eligible for the current cycle . Test Steps: 1. Launch the application using url 2. Enter valid credentials and login to the application. | 1. User should land to profile page. 2. User should get the strength card in same order as it displays in start screen. | 1. User landed to the profile page. 2. Working as Expected. | Pass |  | 2022-04-06
4 | Card strength display in print page | Precondition: 1. User should be live user. 2. User should be eligible for the current cycle . Test Steps: 1. Launch the application using url 2. Enter valid credentials and login to the application. 3. Go to profile page . 4. Click on print. | 1. User should land to the profile page. 2. User should see the card strength in same order as displayed in profile page. | 1. User landed to the profile page. 2. Working as Expected. | Pass |  | 2022-04-06